## Instructions
Annual Intergovernmental Affairs Strategic Plan Tracker
Intergov Association Resource Library. Companion to the Annual Strategic Plan Template.
SETUP: complete these cells first
Organization |  | Name that appears on the dashboard.
Office |  | Your unit within the organization.
Plan year |  | The year the plan covers, for example 2027.
Plan year starts in month (1 to 12) | 1 | 1 for a calendar-year plan. 7 for a plan that starts in July. Drives quarter labels.
Report as-of date |  | Leave blank to use today's date. Enter a date to freeze the reporting position.
Risk review interval (days) | 90 | A risk not reviewed within this many days is flagged.
Date used for all reporting | 2026-10-26 | Calculated. Every overdue and due-soon flag measures against this date.
HOW TO USE THE WORKBOOK
Step 1 | Complete the setup cells above. Leave the as-of date blank for everyday use. Enter a date when you prepare a quarterly report so figures match what leadership saw.
Step 2 | Enter objectives first. Their IDs (OBJ-1, OBJ-2, and so on) feed the dropdowns on every other sheet. Four to seven objectives is a workable range.
Step 3 | Add people to the People list on the Lists sheet so Lead and Owner entries stay consistent. Enter governments on Relationships and bills, rules, grants, and agreements on Priorities.
Step 4 | Break each objective into milestones: dated results with one owner. Mark dates other governments set as Fixed External Date, and dates you expect but no one has confirmed as Assumed External Date.
Step 5 | Log engagement on Actions as it happens. Give each completed action an outcome. A completed action linked to a Relationship ID updates that relationship's Last Contact and Contact Status automatically.
Step 6 | Record risks with an early warning indicator you can observe. When an issue needs a decision above your level, log it on Escalations with the decision requested and the date you need it.
Step 7 | At each quarterly review, add one row per objective on Quarterly Review, then update the Status on Objectives to match. Move dates with Revised Due Date so the original date stays visible.
Step 8 | Read the Dashboard. It summarizes the other sheets and cannot be edited. Use the filter arrows on any table header to sort or filter.
WORKSHEETS
Sheet | What it is for | Who updates it | How often
Dashboard | Summary of the whole workbook for leadership and for your own review. | No one. Calculated. | Read weekly
Objectives | The plan's commitments, with progress calculated from milestones and risks. | Plan owner and objective leads | At each review
Relationships | Priority governments, who owns each, and whether contact is keeping pace. | Relationship leads | Monthly
Priorities | Bills, rules, grants, approvals, and agreements with positions and key dates. | Item leads | Weekly in session
Actions | Engagement log. Feeds Last Contact on Relationships. | Whoever acts | As it happens
Milestones | Dated results and dependencies. Feeds progress on Objectives. | Milestone owners | Weekly or biweekly
Risks | Register of what could stop an objective, with early warning indicators. | Risk owners | Monthly, formal each quarter
Escalations | Decisions requested above your level and whether they arrived in time. | Plan owner | As raised
Quarterly Review | The permanent record of each quarter's status, evidence, and adjustments. | Plan owner | Each quarter
Definitions | What each status, tier, rating, and flag means, and a field guide. | Reference | Read once
Lists | Dropdown choices and the People list. | Plan owner | When names or terms change
CONVENTIONS AND LIMITS
• | Identifiers: EP-1 executive priority, OBJ-1 objective, REL-01 relationship, LEG-01 legislative item, ADM-01 administrative item, MS-001 milestone, ACT-001 action, RSK-01 risk, ESC-01 escalation. Number each type in sequence, never reuse an ID after an item closes, and use the same ID in the Word plan. The Data Checks on the Dashboard flag duplicate IDs, references to records that do not exist, LEG or ADM prefixes that do not match the Track, missing owners, and dates that do not make sense.
• | The Word plan holds executive summaries. This workbook holds the full registers: every contact, milestone, risk, and action. Update the workbook as work happens and the plan at each quarterly review.
• | Navy headers mark input columns. Slate headers over gray cells mark calculated columns. Do not type over calculated cells.
• | Status colors always appear with the status word. Nothing in the workbook depends on color alone.
• | Each data sheet is an Excel table with formulas prefilled for 15 objectives, 40 relationships, 30 priorities, 120 actions, 80 milestones, 30 risks, 25 escalations, and 40 review rows. To add rows beyond that, select the last row of the table and copy it down, or drag the table's lower-right handle. The dashboard picks up added rows.
• | Dropdown lists for Lead and Owner accept names that are not on the People list after a warning. All other dropdowns accept only listed values.
• | Built for Microsoft Excel 2016 or later, including Microsoft 365. It uses no macros, add-ins, or external connections. Google Sheets does not support the table references used here.
• | The dashboard lists the first ten objectives. Counts and charts include every row.

## Dashboard
Executive Dashboard
¦ ¦ Plan year ¦ Report date Oct 26, 2026 ¦ Quarter Q4
Every figure calculates from the worksheets. Set the report date on the Instructions sheet.
OBJECTIVES AT RISK OR OFF TRACK |  | OVERDUE MILESTONES |  | OPEN HIGH-EXPOSURE RISKS |  | RELATIONSHIPS OVERDUE FOR CONTACT |  | PRIORITIES NEEDING ATTENTION |  | ESCALATIONS AWAITING DECISION
0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
of 0 objectives |  | Due within 14 days: 0 |  | Escalated: 0 |  | No contact logged: 0 |  | Clearance needed: 0 |  | Past due: 0
OBJECTIVES
ID | Objective |  |  |  | Lead | Status | Target date | Milestones done | Percent complete | Overdue milestones | Open high risks
MILESTONES BY QUARTER | [6 empty] | OBJECTIVES BY STATUS
Quarter | Total | Complete | Open, on schedule | Overdue | Slipped from original date |  | Status |  | Count
Q1 | 0 | 0 | 0 | 0 | 0 |  | Not Started |  | 0
Q2 | 0 | 0 | 0 | 0 | 0 |  | On Track |  | 0
Q3 | 0 | 0 | 0 | 0 | 0 |  | At Risk |  | 0
Q4 | 0 | 0 | 0 | 0 | 0 |  | Off Track |  | 0
Total | 0 | 0 | 0 | 0 | 0 |  | Complete |  | 0
Completed after their due date: 0 of 0 completed milestones. | [6 empty] | Deferred |  | 0
[7 empty] | Total |  | 0
RELATIONSHIPS: CONTACT STATUS BY TIER | [7 empty] | POSTURE, TIERS 1 AND 2
Tier |  | Current | Due soon | Overdue | No contact logged | Total |  | Posture |  | Count
Tier 1 Strategic |  | 0 | 0 | 0 | 0 | 0 |  | Aligned |  | 0
Tier 2 Priority |  | 0 | 0 | 0 | 0 | 0 |  | Mixed |  | 0
Tier 3 Maintain |  | 0 | 0 | 0 | 0 | 0 |  | Divergent |  | 0
Tier 4 Monitor |  | 0 | 0 | 0 | 0 | 0 |  | Unknown |  | 0
Total |  | 0 | 0 | 0 | 0 | 0
As Needed relationships are not counted in the status columns: 0. Strained relationships: 0.
LEGISLATIVE AND ADMINISTRATIVE PRIORITIES
Track |  | Open items | Clearance needed | Key date within 14 days |  | Next five key dates | Matter |  |  | Date | Days
Legislative |  | 0 | 0 | 0
Administrative |  | 0 | 0 | 0
Total |  | 0 | 0 | 0
Positions by status: Support 0, Oppose 0, Amend 0, Seek 0, Monitor 0, Undecided 0
RISKS (RIGHT: TOP FIVE OPEN RISKS BY EXPOSURE)
Open risks by rating |  | Count |  | ID | Risk |  |  |  | Rating | Owner | Status
High |  | 0
Moderate |  | 0
Low |  | 0
Review overdue or none |  | 0
Escalated risks |  | 0
NEXT FIVE OPEN MILESTONES (OVERDUE FIRST)
ID | Milestone |  |  |  | Objective | Owner |  | Due | Schedule flag |  | Critical path
ENGAGEMENT ACTIONS BY QUARTER | [6 empty] | ESCALATIONS
Quarter | Complete | Planned or in progress | Overdue | Deferred or cancelled |  |  | Response status |  |  | Count
Q1 | 0 | 0 | 0 | 0 |  |  | Open |  |  | 0
Q2 | 0 | 0 | 0 | 0 |  |  | Past Due |  |  | 0
Q3 | 0 | 0 | 0 | 0 |  |  | Resolved |  |  | 0
Q4 | 0 | 0 | 0 | 0 |  |  | Average days to resolve
Total | 0 | 0 | 0 | 0
Overdue means Planned or In Progress with a date before the report date.
DATA CHECKS
Check | [6 empty] | Count | Result
Objectives with no milestones | [6 empty] | 0 | OK
Objectives with no lead | [6 empty] | 0 | OK
Open milestones with no owner or no due date | [6 empty] | 0 | OK
Open high risks with no mitigation entered | [6 empty] | 0 | OK
Tier 1 and 2 relationships with no contact logged | [6 empty] | 0 | OK
Objective status differs from the latest quarterly review | [6 empty] | 0 | OK
Milestones that depend on an unfinished milestone already overdue | [6 empty] | 0 | OK
Records sharing an ID with another record on the same sheet | [6 empty] | 0 | OK
Records pointing to an objective ID that does not exist | [6 empty] | 0 | OK
Other cross-references to a record that does not exist | [6 empty] | 0 | OK
Priority IDs that do not match the Track (LEG or ADM) | [6 empty] | 0 | OK
Open risks, open actions, and escalations with no owner | [6 empty] | 0 | OK
Dates that do not make sense (text, completed before raised, completed but not marked Complete) | [6 empty] | 0 | OK

## Objectives
Strategic Objectives
Four to seven outcomes the plan commits to. Each objective needs one lead, a measurable result, and a date.
Navy headers: enter data. Slate headers with gray cells: calculated, do not overwrite. Row 4 (italic) shows the expected format and is not part of the table.
OBJ-1 | Obtain a funding commitment from a partner government for a priority project | Legislative | The partner government commits funds in writing before the application deadline. | Written funding commitment on file | No commitment today | Commitment received by the application deadline | EP-1 | Name | Name | 2027-01-04 | 2027-05-28 | On Track | One or two sentences leadership should know now.
ID | Objective | Type | Intended Outcome | Success Measure | Baseline | Target | Executive Priority | Lead | Support | Start Date | Target Date | Status | Status Note | Days to Target | Milestones | Milestones Complete | Percent Complete | Overdue Milestones | Open High Risks | Latest Review Status

## Relationships
Priority Governmental Relationships
Where relationship effort goes, who owns each relationship, and whether contact is keeping pace with the cadence you set.
Navy headers: enter data. Slate headers with gray cells: calculated, do not overwrite. Row 4 (italic) shows the expected format and is not part of the table.
REL-01 | State department of transportation | State | Name or title | Program director | Name | Tier 1 Strategic | Aligned | Working | A signed agreement and a formal funding request | Written funding commitment before the application is finalized | OBJ-3 | Monthly | Context a successor would need.
ID | Government or Institution | Level | Key Contact | Contact Title | Our Lead | Tier | Posture | Relationship Health | What They Need From Us | What We Need From Them | Objective ID | Cadence | Notes | Cadence Days | Last Contact | Days Since Contact | Contact Status | Next Planned Contact

## Priorities
Legislative and Administrative Priorities
Bills, budget items, rules, grants, approvals, and agreements you are working, with positions, clearance, and key dates.
Navy headers: enter data. Slate headers with gray cells: calculated, do not overwrite. Row 4 (italic) shows the expected format and is not part of the table.
LEG-01 | Legislative | Bill | HB 100, Local Funding Authorization | State legislature | State | Support | OBJ-1 | Name | Active Consideration | Cleared | 2027-04-14 | Committee vote | Enactment with the authority and terms the objective requires | Competing interests, conditions, and links to other items.
ID | Track | Item Type | Measure or Matter | Body or Agency | Level | Our Position | Objective ID | Lead | Stage | Clearance | Next Key Date | Key Date Description | Desired Outcome | Notes | Days to Key Date | Date Flag | Open | Attention | Open Actions | Upcoming Rank
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Actions
Engagement and Action Log
Meetings, briefings, testimony, and other engagement. Completed actions update Last Contact on the Relationships sheet.
Navy headers: enter data. Slate headers with gray cells: calculated, do not overwrite. Row 4 (italic) shows the expected format and is not part of the table.
ACT-001 | 2027-03-08 | Meeting | Meet agency program staff on the funding commitment | OBJ-3 | REL-05 | ADM-02 | Name | Complete | What changed as a result of the meeting. | Send the agreement timeline to agency staff
ID | Date | Action Type | Description | Objective ID | Relationship ID | Priority ID | Owner | Status | Outcome or Result | Next Step | Quarter | Timing Flag | Days Overdue

## Milestones
Milestones and Deadlines
Dated results that show whether each objective will land on time. Record schedule moves in Revised Due Date.
Navy headers: enter data. Slate headers with gray cells: calculated, do not overwrite. Row 4 (italic) shows the expected format and is not part of the table.
MS-001 | Written funding commitment received | OBJ-3 | Internal Target | Name | 2027-07-30 |  | Not Started |  | MS-028 | Yes | Blockers, assumptions, or what the date depends on.
ID | Milestone | Objective ID | Type | Owner | Due Date | Revised Due Date | Status | Completed Date | Depends On | Critical Path | Notes | Effective Due | Quarter | Slip Days | Days to Due | Schedule Flag | Dependency Status | Open Rank

## Risks
Risk Register
What could stop an objective, how you will know early, and what you will do. Review every quarter.
Navy headers: enter data. Slate headers with gray cells: calculated, do not overwrite. Row 4 (italic) shows the expected format and is not part of the table.
RSK-01 | The bill fails or is amended to remove the authority, leaving the objective without a funding source. | Legislative | OBJ-1 | Moderate | High | Hearing not noticed, or amendments filed by an opposing member. | Weekly vote count. Prepare an alternate funding scenario in parallel. | Name | Mitigating | None | 2026-12-14 | 2027-04-05
ID | Risk Statement | Category | Objective ID | Likelihood | Impact | Early Warning Indicator | Mitigation or Contingency | Owner | Status | Escalation Level | Date Identified | Last Reviewed | Likelihood Score | Impact Score | Exposure | Rating | Days Since Review | Review Flag | Risk Rank

## Escalations
Escalation Log
Issues taken to a decision-maker, the decision requested, and whether the answer arrived in time.
Navy headers: enter data. Slate headers with gray cells: calculated, do not overwrite. Row 4 (italic) shows the expected format and is not part of the table.
ESC-01 | 2027-03-18 | RSK-04 | OBJ-4 | Two partner governments are deadlocked on cost allocation. | Executive Sponsor | Name | Authorize a negotiating range for our share. | 2027-04-02 | 2027-04-01 | What was decided, by whom, with any conditions.
ID | Date Raised | Risk ID | Objective ID | Issue | Escalated To | Raised By | Decision or Direction Requested | Response Due | Date Resolved | Decision Made | Response Status | Days Open | Days Past Due

## Quarterly Review
Quarterly Performance Review
One row per objective per quarter. Record the status, the evidence, the variance, and what you changed.
Navy headers: enter data. Slate headers with gray cells: calculated, do not overwrite. Row 4 (italic) shows the expected format and is not part of the table.
Q1 | OBJ-3 |  | 2027-04-06 | At Risk | Events, decisions, and documents that support the status. | Where actual differs from plan, and why. | What changed in the plan as a result. | A decision with a date, or None. | Names of attendees
Quarter | Objective ID | Objective | Review Date | Status | Evidence of Progress | Variance and Cause | Adjustment Made | Leadership Decision Needed | Reviewed By | Key | Prior Status | Movement

## Definitions
Definitions and Field Guide
What each status, tier, rating, and flag means, and what to enter in each input column.
OBJECTIVE STATUS
Status |  | Meaning
Not Started |  | Work has not begun, or the start date has not arrived.
On Track |  | Milestones are on schedule and no open issue threatens the target date or outcome.
At Risk |  | A milestone is late, a dependency is unresolved, or an assumption is in doubt. The target can still be met with an adjustment or a decision.
Off Track |  | The target date or outcome will not be met without a change in scope, schedule, or a leadership decision.
Complete |  | The outcome occurred and the success measure was met.
Deferred |  | Leadership deliberately postponed the objective. Record who decided and when in the status note.
MILESTONES
Term |  | Meaning
Fixed External Date |  | A date another government or body sets and you cannot move, such as a filing deadline or a hearing.
Assumed External Date |  | A date you expect another party to set but no one has confirmed. Treat as an assumption and revisit when confirmed.
Internal Target |  | A date you set for your own work.
Decision Point |  | A date by which someone must decide for the work to continue.
Delayed |  | Running late with a new date set in Revised Due Date.
Blocked |  | Cannot proceed until another party acts. Name the party in Notes.
Critical Path |  | Yes means a slip in this milestone moves the objective's target date.
RELATIONSHIPS
Tier | Default contact standard | Meaning
Tier 1 Strategic | Monthly or more often; weekly during active sessions | The relationship decides whether an objective succeeds.
Tier 2 Priority | Monthly to quarterly | Important to one or more objectives, but not decisive alone.
Tier 3 Maintain | Quarterly | Useful to keep warm. Needed on specific matters.
Tier 4 Monitor | Semiannual or as needed | Watch for developments. No active engagement planned.
Posture |  | Meaning
Aligned |  | Shares your position on current matters.
Mixed |  | Aligned on some matters and divergent on others. Name both in Notes.
Divergent |  | Opposes your position on a matter that affects an objective.
Unknown |  | Not yet assessed. Treat as a gap to close, not as neutral.
Relationship Health |  | Meaning
Strong |  | Open channel, mutual trust, and prompt response.
Working |  | Functional and professional. Responsiveness varies.
Strained |  | Recent conflict, missed commitments, or poor responsiveness.
New |  | No track record yet.
Dormant |  | No active relationship.
Contact Status (calculated) |  | Meaning
Current |  | Days since the last completed contact are within 75 percent of the cadence.
Due Soon |  | Between 75 and 100 percent of the cadence has passed.
Overdue |  | More days have passed than the cadence allows.
No Contact Logged |  | No completed, non-internal action is linked to this relationship.
As Needed |  | Cadence is As Needed, so no clock runs.
Last Contact |  | The latest date of a Complete action linked to the Relationship ID. Internal Clearance actions are excluded.
PRIORITIES
Term |  | Meaning
Track |  | Legislative means action by a legislative body. Administrative means action by an agency, executive, or other decision-maker outside a legislature.
Our Position |  | Support, Oppose, Amend (support only if changed), Seek (you are asking for a result), Monitor (watch only), Undecided (no cleared position yet).
Clearance |  | Whether the position has cleared your internal process. Monitor items do not need clearance.
Open |  | 1 unless the stage is Resolved Favorable, Resolved Unfavorable, or Inactive.
Attention (calculated) |  | Clearance Needed: an open item with a position other than Monitor that is not Cleared. Key Date Within 14 Days or Key Date Passed: based on Next Key Date.
RISKS
Term |  | Meaning
Likelihood and Impact |  | Low scores 1, Moderate 2, High 3.
Exposure (calculated) |  | Likelihood score multiplied by Impact score. Possible values are 1, 2, 3, 4, 6, and 9.
Rating (calculated) |  | High for exposure of 6 or more, Moderate for 3 or 4, Low for 1 or 2. A sorting aid to focus review time, not a measure of performance.
Review Flag (calculated) |  | Review Overdue when the last review is older than the risk review interval on the Instructions sheet. Never Reviewed when no review date is entered.
Escalation Level |  | The highest level this risk has been raised to. Log each escalation on the Escalations sheet.
CALCULATED FLAGS
Flag | Where | Meaning
Overdue | Milestones | Not complete and the effective due date is before the report date.
Due Within 14 Days | Milestones | Not complete and due within 14 days of the report date.
Completed Late | Milestones | Completed after the effective due date. A milestone moved with Revised Due Date is judged against the revised date.
Overdue | Actions | Planned or In Progress with a date before the report date.
Past Due | Escalations | No resolution date and the response date has passed.
Improved, Declined, Unchanged | Quarterly Review | Compares status with the prior quarter using this order: Off Track, At Risk, On Track, Complete.
Percent Complete | Objectives | Completed milestones divided by all milestones linked to the objective. It measures schedule progress, not whether the outcome will occur.
FIELD GUIDE: WHAT TO ENTER IN EACH INPUT COLUMN
Sheet and column | Example | What to enter
Objectives: ID | OBJ-1 | Short unique code. Every other sheet picks from these IDs, so enter objectives first.
Objectives: Objective | Obtain a funding commitment from a partner government for a priority project | One sentence naming the result, not the activity.
Objectives: Type | Legislative | The kind of work that dominates the objective.
Objectives: Intended Outcome | The partner government commits funds in writing before the application deadline. | The end state a person outside your office could verify.
Objectives: Success Measure | Written funding commitment on file | What you will check to decide whether the outcome occurred.
Objectives: Baseline | No commitment today | Where things stand when the plan year starts.
Objectives: Target | Commitment received by the application deadline | The result and date that count as success.
Objectives: Executive Priority | EP-1 | The leadership priority this objective serves, using the ID from the plan.
Objectives: Lead | Name | One accountable person.
Objectives: Support | Name | Other people who carry part of the work.
Objectives: Start Date | Jan 4, 2027 | When work begins.
Objectives: Target Date | May 28, 2027 | When the outcome is due.
Objectives: Status | On Track | Your judgment as of the last review. See Definitions.
Objectives: Status Note | One or two sentences leadership should know now. | One or two sentences leadership should know now.
Relationships: ID | REL-01 | Short unique code.
Relationships: Government or Institution | State department of transportation | The institution, not an individual.
Relationships: Level | State | Level of government.
Relationships: Key Contact | Name or title | Primary counterpart. Use a title if the name is not confirmed.
Relationships: Contact Title | Program director | Counterpart's position.
Relationships: Our Lead | Name | The one person who owns the relationship on our side.
Relationships: Tier | Tier 1 Strategic | Where relationship effort goes. See Definitions.
Relationships: Posture | Aligned | Their position on our current agenda.
Relationships: Relationship Health | Working | The quality of the working relationship, separate from agreement on issues.
Relationships: What They Need From Us | A signed agreement and a formal funding request | Their interests and requirements, stated from their side.
Relationships: What We Need From Them | Written funding commitment before the application is finalized | The specific ask, tied to an objective.
Relationships: Objective ID | OBJ-3 | The objective this relationship matters most to.
Relationships: Cadence | Monthly | How often you should be in contact. Drives the contact status.
Relationships: Notes | Context a successor would need. | Context a successor would need.
Priorities: ID | LEG-01 | Short unique code. LEG for legislative, ADM for administrative is a useful habit.
Priorities: Track | Legislative | Legislative: action by a legislative body. Administrative: action by an agency or executive body.
Priorities: Item Type | Bill | The kind of matter.
Priorities: Measure or Matter | HB 100, Local Funding Authorization | Bill number and short title, rule docket, grant round, or agreement.
Priorities: Body or Agency | State legislature | Who decides.
Priorities: Level | State | Level of government that decides.
Priorities: Our Position | Support | Position as cleared. Use Undecided until leadership clears one.
Priorities: Objective ID | OBJ-1 | The objective this item serves.
Priorities: Lead | Name | One accountable person.
Priorities: Stage | Active Consideration | Where the matter stands. Resolved or Inactive items drop out of the open counts.
Priorities: Clearance | Cleared | Whether the position has cleared your internal process.
Priorities: Next Key Date | Apr 14, 2027 | The next date that changes what you must do.
Priorities: Key Date Description | Committee vote | What happens on that date.
Priorities: Desired Outcome | Enactment with the authority and terms the objective requires | What a good result looks like, specific enough to judge.
Priorities: Notes | Competing interests, conditions, and links to other items. | Competing interests, conditions, and links to other items.
Actions: ID | ACT-001 | Short unique code.
Actions: Date | Mar 8, 2027 | Actual date for completed actions. Planned date for upcoming ones.
Actions: Action Type | Meeting | Internal Clearance is internal work and does not count as contact with another government.
Actions: Description | Meet agency program staff on the funding commitment | What was or will be done, with whom.
Actions: Objective ID | OBJ-3 | The objective served.
Actions: Relationship ID | REL-05 | The government or institution involved. Leave blank for internal work.
Actions: Priority ID | ADM-02 | The legislative or administrative item involved, if any.
Actions: Owner | Name | Who does it.
Actions: Status | Complete | Planned, In Progress, Complete, Deferred, or Cancelled.
Actions: Outcome or Result | What changed as a result of the meeting. | What happened and what changed, not a description of the meeting.
Actions: Next Step | Send the agreement timeline to agency staff | The single next action this created. Log it as its own Planned row.
Milestones: ID | MS-001 | Short unique code.
Milestones: Milestone | Written funding commitment received | A dated result, not an activity. Something is either done or it is not.
Milestones: Objective ID | OBJ-3 | The objective served.
Milestones: Type | Internal Target | Fixed and Assumed external dates are set by others. Internal targets are yours.
Milestones: Owner | Name | One accountable person.
Milestones: Due Date | Jul 30, 2027 | The original date. Do not overwrite it when the date moves.
Milestones: Revised Due Date |  | Enter a new date here when the schedule moves. The original stays visible.
Milestones: Status | Not Started | Not Started, In Progress, Complete, Delayed, or Blocked.
Milestones: Completed Date |  | Enter when status is Complete.
Milestones: Depends On | MS-028 | The milestone that must finish first, if any.
Milestones: Critical Path | Yes | Yes if a slip here moves the objective's target date.
Milestones: Notes | Blockers, assumptions, or what the date depends on. | Blockers, assumptions, or what the date depends on.
Risks: ID | RSK-01 | Short unique code.
Risks: Risk Statement | The bill fails or is amended to remove the authority, leaving the objective without a funding source. | Cause, event, and effect in one or two sentences.
Risks: Category | Legislative | The kind of risk.
Risks: Objective ID | OBJ-1 | The objective at risk.
Risks: Likelihood | Moderate | Your judgment over the plan year.
Risks: Impact | High | Effect on the objective if the risk occurs.
Risks: Early Warning Indicator | Hearing not noticed, or amendments filed by an opposing member. | An observable sign the risk is becoming real.
Risks: Mitigation or Contingency | Weekly vote count. Prepare an alternate funding scenario in parallel. | What you do now and what you do if it happens.
Risks: Owner | Name | Who watches the indicator and acts.
Risks: Status | Mitigating | Open, Mitigating, Escalated, Realized, or Closed.
Risks: Escalation Level | None | Highest level this risk has been raised to.
Risks: Date Identified | Dec 14, 2026 | When it entered the register.
Risks: Last Reviewed | Apr 5, 2027 | Update at each review, even if nothing changed.
Escalations: ID | ESC-01 | Short unique code.
Escalations: Date Raised | Mar 18, 2027 | When it went to the decision-maker.
Escalations: Risk ID | RSK-04 | The risk this relates to, if any.
Escalations: Objective ID | OBJ-4 | The objective affected.
Escalations: Issue | Two partner governments are deadlocked on cost allocation. | What happened and why it cannot be resolved at your level.
Escalations: Escalated To | Executive Sponsor | Who must decide.
Escalations: Raised By | Name | Who brought it forward.
Escalations: Decision or Direction Requested | Authorize a negotiating range for our share. | The specific decision. A request with no decision attached is a status update.
Escalations: Response Due | Apr 2, 2027 | The date you need an answer to protect a milestone.
Escalations: Date Resolved | Apr 1, 2027 | Enter when the decision is received.
Escalations: Decision Made | What was decided, by whom, with any conditions. | What was decided, by whom, with any conditions.
Quarterly Review: Quarter | Q1 | Plan quarter being reviewed.
Quarterly Review: Objective ID | OBJ-3 | One row per objective per quarter.
Quarterly Review: Review Date | Apr 6, 2027 | Date of the review meeting.
Quarterly Review: Status | At Risk | Status as agreed at the review. Update the Objectives sheet to match.
Quarterly Review: Evidence of Progress | Events, decisions, and documents that support the status. | Facts that support the status: events, decisions, documents.
Quarterly Review: Variance and Cause | Where actual differs from plan, and why. | Where actual differs from plan and why.
Quarterly Review: Adjustment Made | What changed in the plan as a result. | What changed in the plan as a result. Record it in the plan as well.
Quarterly Review: Leadership Decision Needed | A decision with a date, or None. | A decision with a date, or None.
Quarterly Review: Reviewed By | Names of attendees | Who attended.

## Lists
Lists
Dropdown choices used across the workbook. Edit wording here to match your organization. Keep the order of the status rank list.
Do not delete or rename a column header. Change a list item only if no rows use the old value, or update those rows to match.
lstObjType | lstObjStatus | lstLevel | lstTier | lstPosture | lstHealth | lstTrack | lstItemType | lstPosition | lstStage | lstClearance | lstActionType | lstActionStatus | lstMsType | lstMsStatus | lstYesNo | lstRiskCat | lstLevel3 | lstRiskStatus | lstEscLevel | lstEscTo | lstQuarter | lstStatusRank | lstCadence | lstCadenceDays | People
Legislative | Not Started | Federal | Tier 1 Strategic | Aligned | Strong | Legislative | Bill | Support | Developing | Not Submitted | Meeting | Planned | Fixed External Date | Not Started | Yes | Legislative | Low | Open | None | Office Director | Q1 | Off Track | Weekly | 7
Administrative | On Track | State | Tier 2 Priority | Mixed | Working | Administrative | Budget Item | Oppose | Pending Action | In Review | Briefing | In Progress | Assumed External Date | In Progress | No | Administrative | Moderate | Mitigating | Office Director | Executive Sponsor | Q2 | At Risk | Biweekly | 14
Relationship | At Risk | Tribal | Tier 3 Maintain | Divergent | Strained |  | Rulemaking | Amend | Active Consideration | Cleared | Testimony or Comment | Complete | Internal Target | Complete |  | Relationship | High | Escalated | Executive Sponsor | Chief Executive | Q3 | On Track | Monthly | 30
Intergovernmental Agreement | Off Track | Regional | Tier 4 Monitor | Unknown | New |  | Grant or Funding | Seek | Final Action Pending | On Hold | Written Submission | Deferred | Decision Point | Delayed |  | Fiscal |  | Realized | Chief Executive | Governing Board | Q4 | Complete | Quarterly | 90
Internal Process | Complete | County |  |  | Dormant |  | Permit or Approval | Monitor | Resolved Favorable |  | Call or Correspondence | Cancelled |  | Blocked |  | Legal |  | Closed | Governing Board |  |  |  | Semiannual | 180
| Deferred | Municipal |  |  |  |  | Agreement | Undecided | Resolved Unfavorable |  | Coalition Work |  |  |  |  | Capacity | [6 empty] | As Needed
|  | Special District |  |  |  |  | Policy Guidance |  | Inactive |  | Site Visit |  |  |  |  | Reputational
|  | Other |  |  |  |  | Other |  |  |  | Internal Clearance |  |  |  |  | Schedule | [6 empty] | Days between expected contacts. As Needed has no day count.
Agreement Work
Other
Add names under People. They feed the Lead and Owner dropdowns.